## Project Budget
Budget: Project Plant Pals Operations & Training
[7 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
[7 empty] | 62000 | 0 | 62000
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Milestone 1: Establish a plant delivery and logistics plan
Task 1: Purchase delivery trucks. Purchase two delivery trucks at a cost of $15,000 per truck. | Trucks |  |  | 2 | 15000 |  | 30000 |  | -30000
Task 2:Source packaging materials. Purchase 1,500 boxes at a cost of $2 per box. | Boxes |  |  | 1500 | 2 |  | 3000 |  | -3000
Task 3:Pay delivery drivers. Pay two delivery drivers for ten days (assume eight-hour work days) at a rate of $15 per hour | Delivery Drivers | 160 | 15 |  |  |  | 2400 |  | -2400
-- | [5 empty] | Total | 35400 | 0
Milestone 2:Select and install supply chain management software and equipment.
Task 1: Source vendor (includes setup, installation, and deployment of software and equipment systems): Fixed cost of $15,000. | Source Vendor |  |  |  |  | 15000 | 15000 |  | -15000
-- | [5 empty] | Total | 15000 | 0
Milestone 3:Develop and launch an employee training program.
Task 1: Develop training sessions. Pay the HR specialist $50 per hour for ten days (assume eight-hour workdays). | HR Specialist | 80 | 50 |  |  |  | 4000 |  | -4000
Task 2:Train employees to use the software and equipment. Pay the Training Manager $25 per hour for ten days (assume eight-hour workdays). | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000
Task 3:Monitor employee progress and improve training processes. Pay the Training Manager $25 per hour for another ten days (assume eight-hour workdays). | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000
-- | [5 empty] | Total | 8000 | 0
Reserve buffer | [6 empty] | 3600
TOTAL | [6 empty] | 62000 | 0